King’s Health Partners Clinical Trials Office Monitoring Plan (for Clinical Trials Sponsored by King’s Health Partners)

| Protocol Title |  |
| --- | --- |
| Chief Investigator |  |
| Sponsor |  |
| EudraCT Number |  |
| IRAS Number |  |
| MATTS Number |  |

| Date of Release |  |
| --- | --- |
| Version Number |  |

| Author: | Print name | Sign | Date |
| --- | --- | --- | --- |
| Authorised by: | Print name | Sign | Date – should be same date as version number of document. |

DOCUMENT HISTORY

| Version | Date | Section | Description |
| --- | --- | --- | --- |
| 1.1 | 05Aug08 |  | Initial Release |
| 1.2 | 23Mar10 |  | Document transferred to KHP header information and document key updated to accommodate the new headers and footers. |
| 1.3 | 13Jun12 |  | Administrative changes to KHPCTO |
| 1.4 | 29Aug12 |  | Minor administrative changes |
| 2.0 | 03Dec18 |  | Changes in line with updated SOPs and current practice |
| 3.0 | 18Aug21 |  | Changes in line with updated SOPs and current practice |

This table currently reflects the document history of the Monitoring Plan template and should be replaced with the trial-specific Monitoring Plan document history. If there is an update to a section of the monitoring plan the entire document should be released with a new version number and the document history page completed.

| Document Key |  |
| --- | --- |
| Regular black text | Suggested content |
| Green italics | Instructions |
| Blue Italics | Optional text |
| Note on headers & footers | Front page: The footer at the bottom should detail the KHP-CTO version of the template document. All other pages: The footer should reflect the current version and date of the trial-specific document |

This table is for CRA information only and should be removed prior to finalisation.

TABLE OF CONTENTS

ABBREVIATIONS AND DEFINITIONS	4

1.	TRIAL SUMMARY	5

2.	TRIAL START UP	5

2.1.	KING’S HEALTH PARTNERS CLINICAL TRIAL OFFICE AND TRIAL CONTACTS	5

3.	REFERENCE DOCUMENTATION TO BE USED FOR THIS TRIAL	6

3.1.	PRE-TRIAL COMMENCEMENT	7

3.2.	ESSENTIAL PRE-TRIAL DOCUMENTS	7

3.3.	INITIATION OF THE TRIAL	8

3.4.	CLINICAL RESEARCH ASSOCIATE	8

4.	INVESTIGATIONAL MEDICINAL PRODUCTS	8

4.1.	QP RELEASE OF IMP	9

4.2.	TRACKING OF EXPIRY DATES	8

4.3.	ACCOUNTABILITY, STORAGE AND HANDLING OF IMP	9

4.4.	RETURN AND DESTRUCTION OF IMP	9

5.	MONITORING AND SUPPORT ACTIVITIES DURING THE TRIAL	10

5.1.	TIMING AND FREQUENCY OF MONITORING VISITS	10

5.2.	ACTIVITIES DURING THE MONITORING VISITS	10

5.3.	MONITORING VISIT REPORT AND FOLLOW-UP LETTER	14

5.4.	OTHER CONTACT AND CORRESPONDENCE	14

5.5.	CRF AND QUERY MANAGEMENT	14

6.	TRIAL CLOSE OUT	14

7.	ARCHIVING	15

# ABBREVIATIONS AND DEFINITIONS

| AE | Adverse Event |
| --- | --- |
| CCF | Contact Comment Form |
| CI | Chief Investigator, responsible for overseeing all clinical trial sites in a multi-centre trial. |
| CRA(s) | Clinical Research Associate(s) who monitor clinical trials sponsored or co-sponsored by King’s Health Partner Organisations to ensure GCP compliance |
| CRF | Clinical Record Form/ Case Report Form |
| CRO | Clinical Research Organisation |
| CTA | Clinical Trial Authorisation |
| CV | Curriculum Vitae |
| DCF | Data Clarification Form |
| DSMB | Data Monitoring Committee |
| FDA | Food and Drug Administration (US regulatory agency) |
| GCP | Good Clinical Practice |
| HRA | Human Research Authority |
| MHRA | Medicines and Healthcare products Regulatory Agency |
| MVR | Monitoring Visit Report |
| ICF | Informed Consent Form |
| IMP | Investigational Medicinal Product |
| Investigator | Clinician responsible for running a clinical trial. Sub-Investigator may be used to describe additional clinicians who assist in the running of a clinical trial. |
| ISF | Investigator Site File |
| IVRS | Interactive Voice Response System |
| King’s Health Partners | King’s Health Partners Academic Health Science Centre is a pioneering collaboration between one of the King’s College London (University) and three of London’s most successful NHS Foundation Trusts – Guy’s & St Thomas’. King’s College Hospital and the South London & Maudsley. |
| PI | Principal Investigator, responsible for a single clinical trial site in a multi-centre trial. |
| PIS | Patient Information Sheet |
| QA | Quality Assurance |
| QC | Quality Control |
| QM | Quality Manager |
| QP | Qualified Person |
| REC | Research Ethics Committee |
| SAE | Serious Adverse Event |
| SUSAR | Suspected Unexpected Serious Adverse Reaction |
| REC | Research Ethics Committee |
| R&D | Research & Development |
| TMF | Trial Master File |
| KHP-CTO | King’s Health Partners Clinical Trials Office |

# TRIAL SUMMARY

| Primary objective of trial |  |
| --- | --- |
| Trial timelines | FPFV to EOT |
| Planned number of subjects in the trial |  |
| Number of centres (If multi centre) |  |
| Number of subjects per site (If multi centre) |  |
| Subject numbering system | How will subject numbers be allocated |
| CRF | Paper / Electronic & name of system |
| Data entry and query responsibilities | External management company or internal by site staff |
| Randomisation |  |
| DMC | Data review intervals if applicable |
| TSC | Data review intervals if applicable |

(Table may be amended as necessary to include further trial specific details)

# TRIAL START UP

KING’S HEALTH PARTNERS CLINICAL TRIALS OFFICE AND TRIAL CONTACTS

Regarding quality and monitoring issues the CRA is the first line of contact for trial site staff and investigators; the second line of contact is the Quality Manager. In a multicentre trial, the first point of contact for trial sites regarding any other issues is the Trial Management Team.

Contact Details

| Job Title | Name | Contact Details |
| --- | --- | --- |
| CRA | KHP-CTO CRA | Floor 16, Guy’s Tower Wing T: +44 (0)20 7188 9574 F: +44 (0)20 7188 8330 E: khpcto.crateam@kcl.ac.uk |
| Quality Manager |  |  |
| Pharmacovigilance | KHP-CTO | F: 0207 188 8330 E: jcto.pharmacovigilance@kcl.ac.uk |
| R&D |  |  |
| Pharmacy |  |  |
| External Partners e.g. CROs, IMP management/provision, CTUs, Emergency Unblinding, Laboratory |  |  |

Add additional rows as appropriate.

# REFERENCE DOCUMENTATION TO BE USED FOR THIS TRIAL

Where there are no SOPs in place for managing a trial the KHP-CTO SOPs and guidelines will be followed. All trial-specific SOPs will be reviewed by the CRA, including all amendments, to ensure accuracy – please list them here. Delete any SOPs that are not relevant for the trial but include a statement about any applicable SOPs from external partners e.g. if a CTU is conducting initiation or monitoring visits, .building the eCRF / randomisation system or a co-sponsor has been delegated responsibilities for the CTA application / managing the TMF

| SOP Title | Author Department/Company |
| --- | --- |
| Pharmacovigilance and Safety Reporting Policy | KHP-CTO |
| 2.0 Clinical Trials Training | KHP-CTO |
| 3.0 Clinical Trial Monitoring | KHP-CTO |
| 4.0 Archiving of Clinical Trial Data and Essential Documentation | KHP-CTO |
| 5.0 Creation and Maintenance of TMFs and Essential Documentation | KHP-CTO |
| 6.0 Notification of Serious Breach of GCP or Trial Protocol | KHP-CTO |
| 7.0 Obtaining Informed Consent for Clinical Trials | KHP-CTO |
| 8.0 Case Report Form Design | KHP-CTO |
| 9.0 Writing a GCP compliant Clinical Trial Protocol | KHP-CTO |
| 10.0 Creation and Maintenance of Investigator Brochure | KHP-CTO |
| 11.0 Obtaining Clinical Trial Insurance | KHP-CTO |
| 12.0 Application and Maintenance of a CTA | KHP-CTO |
| 13.0 Investigator Site Initiation | KHP-CTO |
| 14.0 Emergency Code Break |  |
| 15.0 Clinical Trial Computer System Validation | KHP-CTO |
| 16.0 Investigator Site Close-out Procedure | KHP-CTO |
| 17.0 Preparation and Submission of Development Safety Update Reports | KHP-CTO |
| 18.0 Data Management in Clinical Trials | KHP-CTO |
| 19.0 Laboratory Procedures and Sample Analysis in Clinical Trials | KHP-CTO |
| 20.0 Sample Management in Clinical Trials | KHP-CTO |
| 21.0 Vendor Selection and Oversight | KHP-CTO |

Please see the KHP-CTO website for current version information.

PRE-TRIAL COMMENCEMENT

The CRA will assist sites in start-up activities and will, in conjunction with the Quality Manager, ensure that the MHRA CTA Application is completed to a satisfactory standard. Investigators remain responsible for Ethics, HRA and R&D Applications, however CRAs may assist if deemed necessary and appropriate. All contact prior to trial commencement should be documented and filed in the appropriate trial site, TMF or R&D files.

In most multi-centre trials the CI will select the other participating sites; if this is the case the following may be used:

The CI will approach and select all other sites to participate in the trial. The coordinating centre will facilitate application for the relevant local approvals by the individual sites; the nominated CRA/ QM may provide guidance as necessary. All pre-trial contacts will be documented and filed. The R&D department will facilitate the set up and approval of all site agreements and co-sponsorship agreement (if appropriate).

ESSENTIAL PRE-TRIAL DOCUMENTS

Depending on trial classification different documentation may be required. As a rule the checklist from R&D, Ethics and MHRA CTA application forms should be used to determine what is required however it is good practice to maintain a central list

The trial will not be allowed to commence at site until all necessary approvals have been granted and all essential documentation listed in the Site Initiation Visit Checklist is present and has been verified by the CRA. The CRA will also work with the site staff to ensure that all required trial materials are present at site in sufficient quantities prior to initiation. Details of these will be included in the site agreements.

The CRA will also work with the site staff to ensure that all required trial materials are present at site in sufficient quantities prior to initiation. Details of these are found below:

| Material | Re-supply procedure |
| --- | --- |
| Source Data Worksheets | Print off secure computer |
| Lab Kits | Order through pharmacy |

INITIATION OF THE TRIAL

All sites will have an initiation visit prior to the trial starting. Initiation visits will be conducted for each investigator site.  Sites that are not involved with handling or administering IMP will be assessed on a case by case basis by SCRA or delegate.

The following points will be discussed at the initiation meeting (this is the minimum requirement and can be added to as necessary):

- Informed Consent

- Protocol compliance including eligibility review

- Primary and secondary endpoints

- Definitions of source data

- Safety reporting requirements and responsibilities

- Data protection / patient privacy

- CRF completion procedures / Data management

- Randomisation procedures

- Patient compliance

- Handling of samples and scans

- Trial reference manuals (If applicable)

- Pharmacy and dispensing of IMPs (If applicable)

- Maintenance of the TMF/ISF

- Archiving of trial data

- Inspections and audit

- Frequency of monitoring and access to patient data by the Sponsor Organisations

- Serious Breach Reporting

TRIAL CRA

The CRA must be familiar with the protocol and relevant SOPs prior to the start of the trial. If further training is required this will be undertaken with the assistance of the KHP-CTO Training Executives.

If there is a change of a trial CRA, a full handover will be completed and the CI and site teams will be notified. Where the CRA is unexpectedly absent, monitoring cover will be provided by the KHP-CTO.

# INVESTIGATIONAL MEDICINAL PRODUCTS

The CRA will ensure that IMP shipment and receipt documentation are complete, accurate and in accordance with handling requirements of the current SmPC or Investigator’s Brochure.

QP RELEASE OF IMP

The CRA will check that all relevant QP release documentation is in place prior to trial start.

Include details here of how IMP is to be QP released and state what duties the CRA must complete to ensure this is done accurately.

If IMP is manufactured for CT use and provided free by a Pharmaceutical company it is often provided in bulk. It may not be labelled for clinical trial use or packaged appropriately for the trial. Under these circumstances re-packaging and QP release is required. GSTFT is the preferred provider for all Partner Organisations, however an external preferred provider may be used if GSTFT are unable to meet the necessary requirements.

The CRA will liaise with the Clinical Trials Pharmacist to coordinate these activities. Please state who the named QP will be and what documentation is necessary.

If site is purchasing licensed IMP and using it as per label specifications it may not need QP release. If IMP is repackaged or relabelled (the local pharmacy label is allowed without QP) in any way then QP release may be required if not under the regulation 37 exemption. In addition, QP release will be required if the co-ordinating centre is distributing IMP to other participating sites in a multi-centre trial.

Example of text if using GMPU: The IMP will be re-packed and relabelled by Guy’s Manufacturing unit and as such every batch will be QP released individually. The co-ordinating centre will distribute IMP to the other participating centres. The Clinical Trials Pharmacies will not use the IMP if QP release documentation is not included with the shipment.

TRACKING OF EXPIRY DATES

The CRA will check the expiry dates of the IMP on a regular basis and work with Pharmacy to ensure that there is sufficient quantity of valid IMP onsite for the continuation of the trial.

ACCOUNTABILITY, STORAGE AND HANDLING OF IMP

The CRA is responsible for checking the IMP accountability and IMP reconciliation of the IMP both at individual (amount dispensed/used/returned by subject) and site level (total delivered, used, unused, and returned/destroyed by trial site). The CRA will also check that the IMP is being stored and handled according to the requirements of the protocol information (IB, SmPC, label).

RETURN AND DESTRUCTION OF IMP

The CRA will verify accountability and reconciliation prior to destruction or return as follows: Describe what will be done with used / unused IMP at the site and what must be verified. Please indicate if empty packaging/vials will be retained. If IMP is to be returned to an external partner, please replace blue text below with full instructions for IMP return.

Pharmacy will destroy returns or expired items as per local Pharmacy SOP and full documentation will be kept in the pharmacy file. Destruction of IMP should not occur until accountability has been completed and approval for destruction given by the Chief Investigator* and the Sponsor Representative i.e. KHP-CTO. Interim accountability and destruction may be permitted.

* The CRA will confirm arrangements for destruction with the CI. The CI will authorise destruction of the trial IMP either on an ongoing basis or once to cover all destruction episodes throughout the trial.

# MONITORING AND SUPPORT ACTIVITIES DURING THE TRIAL

TIMING AND FREQUENCY OF MONITORING VISITS

In most cases the KHP-CTO Monitoring SOP will be used; however, if this is not the case please give details of external guidelines to be used.

The frequency of monitoring visits is determined by a risk assessment of the trial.

The first monitoring visit following initiation of the site and trial commencement will take place within approximately ………. weeks after the inclusion of the first patient may be consent/baseline depending on the trail risk assessment. Subsequent monitoring visits will take place every ………. weeks.

The interval for monitoring visits may be longer or shorter than stated above, dependant on subject enrolment rate, quality issues, trial site compliance or other trial site issues.

Any significant deviation from the planned monitoring timelines will be explained and documented in the monitoring visit report and the monitoring plan amended if appropriate.

If there is an extended gap in trial activity the CRA should ensure that site staff are appropriately trained when trial activities recommence.

Monitoring visits may also be conducted to vendors providing services for the trial e.g. CTU or laboratories. Frequency of the monitoring visits to vendors should be included in this section. Details of activities covered during these visits should be listed in the relevant of section 5.2 inclusive of relevant subsections.

ACTIVITIES DURING THE MONITORING VISITS

The trial CRA will complete the trial monitoring visit log at every visit. The dates on the log should correspond to those on the monitoring visit reports and follow-up correspondence with the site.

In addition to activities specified in the SOPs above the CRA will focus on the following items (these are trial specific and should be amended as stipulated in the Risk Assessment. An example is given below):

- Review data issues

- Informed Consent of enrolled patients’ ICFs and consent process (xx% must be verified)

- Inclusion / Exclusion criteria (xx% must be verified)

- Safety reporting

- Verify CRF and data queries status

- % IMP accountability

- % primary endpoint SDV

- % data entry checks if transcribing data from a paper CRF into a database

- Review of laboratory sample management (e.g. temperature logs, SOPs, deviations)

Any key issues (any issue that would impact on the integrity of data and subject evaluation) identified during the monitoring visit (including non-compliance, discrepancies, suspicion of misconduct or fraud) must be immediately reported to appropriate personnel, documented and followed up to resolution and where applicable corrective and preventative actions must be documented.

    - SOURCE DATA VERIFICATION PLAN

Source data verification will be performed by the trial CRA for (100%) data in the CRF for (100%) of subjects.

If it is observed that an unacceptable level of discrepancies arises the CRA will retrain site staff. If after such retraining data accuracy is still not considered sufficient the CRA will escalate the issue to their line manager and Quality Manager who will review the risk assessment for the trial and the level of monitoring required.

Percentage of required source data verification will be detailed on the trial risk assessment form

If 100% SDV will not be performed on 100% data for all subjects please specify the trial data to be monitored; the percentage of subjects and percentage  of data per subject to be verified and how the plan may be modified based on findings of SDV. If patients selected for 100% SDV withdraw early, judgement will be made on whether further replacement subjects will be selected for 100% monitoring – another patient may be chosen for SDV from the point that the initial patient selected withdrew. .

    - PRIMARY AND SECONDARY END POINT DATA

During monitoring visits the following endpoint data should be verified as per 5.2 / 5.2.1:

State details of what data the CRA should review to verify the primary (and secondary) endpoint data e.g. ensure that relevant tests/assessments are done at the correct time. Include details on any SDV checklists that can be used by the CRA to ensure that all required data is verified. The level of endpoint data to be verified will be listed in the risk assessment for the trial.

    - SOURCE DOCUMENTATION

Define what documents will be considered as source on a source data location list. Identify any sections of the CRF that will be considered as source data (e.g. patient diaries, questionnaires and trial assessments). If appropriate, source data checklists may be used to assist verification. If any source data is in electronic format and will not be printed off to be verified, the CRA must ensure that this is evidenced on the source data location list and that full details of what must be checked and when should be listed above. Any source data worksheets used must be reviewed and approved by the KHP-CTO CRA before use

The following documents will be considered as source data:

- Patient record (including printed scan reports and blood sampling initialled by a trial doctor)

- Patient diaries

- Quality of life questionnaires

- Informed Consent Forms

Information on where to find specific data points for the trial will be detailed on the source data location list stored in the site file.

If sample analysis will only be performed at the end of the trial, and data is not available until after the end of trial, it is acceptable for this data to be imported directly into the database rather than being transcribed into the CRF. Definition of what constitutes source data must be indicated on the Source Data Location List.

If the trial is using a paper CRF for data collection and if sample analysis will only be performed at the end of the trial,  sample analysis data will not available until after the end of trial. Therefore, it is acceptable for this data to be imported directly into the database rather than being transcribed into the paper CRF. Definition of what constitutes source data must be indicated on the Source Data Location List.

- Discuss any deviations or protocol violations with investigator and take action as appropriate (e.g. amendments, inform CI, MHRA or Ethics)

    - STATUS OF TRIAL SUBJECTS

At each monitoring visit and at regular intervals between visits the CRA will contact the sites to discuss the status of trial subjects (screened, treated, ongoing, and discontinued) enrolled into the trial.

    - COMPLIANCE TO TREATMENT REGIMEN AND IMP ACCOUNTABILITY

Specify actions CRA should complete during monitoring visits.

For the patients selected for IMP accountability review, the CRA will verify adherence to the clinical trial protocol and that trial subjects receive correct medication in the correct doses at the correct times. Any discrepancies (missed doses, incorrect timings) will be documented. Insert details of any data critical to evaluation if the IMP (e.g. peak/trough pharmokinetic evaluations, dose in relation to meals).

Documentation for assigned treatment must be consistent across source data, prescriptions, dispensing logs and CRF records. Other documentation may also need to be verified against hospital logs e.g. electronic dispensing print-outs, IVRS confirmation faxes.

State if Pharmacy is not monitored.

    - SAFETY REPORTING

In addition to the above SOPs and the trial protocol the CRA will verify the following:

- All SAEs/follow up reports have been reported to the Sponsor/Chief Investigator/Ethics committee as required by UK regulations.

- All SAEs/follow up reports have been appropriately reported to the funder, if applicable

- All required SAE data are recorded in the CRF and consistent with source data and SAE forms.

- All documentation is filed in the TMF/ ISF.

- All periodic safety updates and summaries are sent to MHRA and Ethics Committee as required.

    - BIOLOGICAL SAMPLES (BLOOD, URINE, PK SAMPLING)

The CRA will verify that the protocol requirements have been met regarding timing, storage, shipping and documentation of biological samples for the percentage of participants selected for 100% SDV.

If applicable: the research laboratory analysing trial samples will be visited at regular intervals throughout the trial. The details of the visit intervals and the information to be reviewed during the visit should be listed here as per RA.

    - TRIAL MASTER FILE (TMF) AND THE INVESTIGATOR SITE FILE (ISF)

Choose the most appropriate wording:

Single Centre Trials

The TMF will be checked for completeness by the CRA at regular intervals throughout the trial.

Multi-centre Trials

The TMF will be maintained by the Chief Investigator and checked for completeness by the CRA at regular intervals during monitoring. The CI will maintain a site-specific TMF file or section for each participating site containing all essential documentation and pertinent correspondence for that site.

Each site will maintain an Investigator Site File for the trial which will also be checked for completeness by the CRA. All administrative documentation and correspondence for the trial should be filed here.

The site-specific TMF section will be reconciled with the site-specific Investigator Site File at regular intervals to ensure that the TMF documentation remains current however no patient identifiable data will be filed in the TMF.

If TMF managed by a CTU

The TMF will be managed by xx. The TMF will be checked for completeness at regular intervals throughout the trial.

Add multi centre info if applicable.

    - FURTHER TRIAL SUPPORT

The CRA may assist the site in compiling and submitting amendments to Ethics Committee and HRA; however, this remains a site responsibility. Amendments required for the MHRA will be facilitated and processed by the CRA and Quality Manager or delegate.

MONITORING VISIT REPORT AND FOLLOW-UP LETTER

The CRA will fully document each monitoring visit in a Monitoring Visit Report or appropriate document which will be reviewed by the Quality Manager or delegate.  Follow-up correspondence will be sent to site in a timely manner after the visit. All follow-up actions will be followed until resolution. All discrepancies that cannot be resolved will be documented in a file note and signed by the CRA, relevant site staff and PI/CI.

OTHER CONTACT AND CORRESPONDENCE

All pertinent correspondence with site staff will be documented appropriately (e.g. follow-up letter, contact comment forms, e-mails) and filed in the TMF/ISF as applicable.

CRF AND QUERY MANAGEMENT

If using a CTU, include details of their SOPs on CRF design and data management.

The CRA will perform SDV as described in 5.2.1. In addition, quality checks will be performed to ensure that the CRFs have been completed in accordance with relevant guidelines. All CRFs monitored during a visit will be detailed in the Monitoring Visit Report or appropriate document.

Optional text to be used if the CRFs/Imaging data must be sent to another site or external data management company.

The CRA will verify that completed CRF/Imaging forms have been sent to …………(insert relevant details) by ……… (e.g. fax).

Include details of who is responsible for data management, how data queries will be raised and closed when resolved e.g. queries raised in the eCRF or will paper queries be raised. Include details on the audit trial for data queries. Include details of query management for any centrally entered data if applicable.

# TRIAL CLOSE OUT

Specify what and how trial materials including any lab samples will be returned, destroyed or retained by the trial site.

At the end of the trial once all data and documentation has been completed the CRA will perform the Close-out Visit (this may be reported on an MVR if no documentation has been developed). The visit will include final review of all trial documentation including Pharmacy files for completeness. After the final visit the CRA will record all information in a written report. Ideally all outstanding actions will be completed prior to the Close-out Visit however the CRA should follow up all ongoing actions until completion ensuring that all correspondence and documentation is filed.

# ARCHIVING

Once all trial actions have been completed and the trial data has been locked the CRA will work with the site staff and the Archive Specialist to archive the trial documentation.